## Features
Story ID | Area | Feature / Story | Impl status | Test coverage | Code refs | Error IDs | Test result | Fix status | Retest result | Notes
US-NU-01 | Notch UI | Hover preview (dwell 120/250ms, fly-by rejection) | implemented | unit+integration | notch/hover.rs, statemachine.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-NU-02 | Notch UI | Click/hotkey expand <=100ms + 20s auto-collapse | implemented | unit | notch/statemachine.rs | E-19 | fail | documented | documented: E-19 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-NU-03 | Notch UI | Menubar/drag misfire suppression | implemented | unit | notch/hover.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-NU-04 | Notch UI | Fullscreen: hidden, hotkey-only | implemented | unit | notch/statemachine.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-NU-05 | Notch UI | Castle position math (6 spots) | implemented | unit | notch/geometry.rs | E-24 | fail | documented | documented: E-24 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-NU-06 | Notch UI | Top-edge flick overshoot | implemented | unit | notch/geometry.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-01 | Capture | Bounded AX walk, text only | implemented | unit | capture/walk_policy.rs | E-33 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-02 | Capture | Default exclusions (pw managers etc.) | implemented | unit | capture/exclusion.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-03 | Capture | Private browsing exclusion | implemented | unit | capture/exclusion.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-04 | Capture | SecureTextField subtree skip | implemented | unit | capture/walk_policy.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-05 | Capture | 98% near-dup collapse + dwell accumulate | implemented | unit | capture/dedup.rs, daemon.rs | E-17 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CAP-06 | Capture | User exclusions (apps/titles) | implemented (no UI) | unit | exclusion.rs, exclusions.rs | E-27 | fail | documented | documented: E-27 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-01 | Memory | Hybrid FTS+vector search, warm-first | implemented | unit+eval+bench | search.rs, vector.rs | E-09,E-34 | fail | documented | documented: E-09,E-34 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-02 | Memory | Off-write-path embedding | implemented | unit | embed_job.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-03 | Memory | Secret redaction before write | implemented | unit | redact.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-04 | Memory | Cold demotion int8 30d | implemented | unit | cold.rs, quantize.rs | E-09 | fail | documented | documented: E-09 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-05 | Memory | SQLCipher encryption + upgrade | implemented | unit | lib.rs (DbKey) |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-06 | Memory | Export / delete-all | BROKEN | unit (gap) | maintenance.rs | E-01,E-14 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MEM-07 | Memory | AI session ingestion | implemented | unit | ai_session.rs, daemon.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-01 | State | Provenance-mandatory inserts | implemented | unit | state.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-02 | State | Local rule extraction EN/JA (Low conf) | implemented | unit x18 | extract.rs | E-35 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-03 | State | Confidence decay + corroboration | implemented | unit (no combo test) | recompute.rs | E-05 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-04 | State | Confidence bands High/Medium/Low gate | implemented | unit | fusion/confidence.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-05 | State | Identity resolution (no mis-merge) | partial | unit x12 | identity.rs | E-21 | fail | documented | documented: E-21 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-06 | State | Overdue/staleness recompute | implemented | unit | recompute.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-ST-07 | State | One-tap resolve from panel | implemented | none (mutations) | daemon.rs, state.rs | E-11 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CF-01 | Fusion | Pre-assembled context actions <=4 | implemented | unit | assemble.rs, daemon.rs | E-11,E-36 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CF-02 | Fusion | Never-empty panel fallback | implemented | unit | assemble.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CF-03 | Fusion | L1-never-sends (structural) | implemented | unit x5 layers | permission.rs + invariant4.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-AG-01 | Agents | L1/L2/L3 execution engine | implemented | unit | engine.rs | E-22 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-AG-02 | Agents | L3 full-preview approval queue | implemented | unit x11 | approval.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-AG-03 | Agents | Send exec + digest-only trace | implemented | unit x9 | send_exec.rs | E-06 | fail | documented | documented: E-06 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-AG-04 | Agents | 7 preset agents | partial (table only) | unit | presets.rs | E-20 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-AG-05 | Agents | Composio failure -> draft fallback | implemented | unit | composio.rs, send_exec.rs | E-06 | fail | documented | documented: E-06 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DC-01 | Dream | Gate: idle/lock + power + window | implemented | unit x8 | dreamcycle/gate.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DC-02 | Dream | Resumable 6-job plan | implemented | unit | plan.rs, run.rs, jobs.rs | E-37 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DC-03 | Dream | Batch health amber/red, local never blocked | implemented | unit | health.rs, llm/mod.rs | E-38 | fail | documented | documented: E-38 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MB-01 | Brief | Morning Brief assembly + provenance | implemented | unit x8 | brief.rs | E-19b | fail | documented | documented: E-19b | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MB-02 | Brief | Degraded brief (never empty) | implemented | unit | brief.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-01 | Meeting | Ships off, fail-closed settings | implemented | unit x14 | meeting/settings.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-02 | Meeting | Detection (mic+app+URL), 10s offer | implemented | unit x20 | meeting/detect.rs | E-02 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-03 | Meeting | Recording unreachable without offer | implemented | unit+e2e | meeting/statemachine.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-04 | Meeting | Audio never leaves RAM | implemented | unit | audio/* |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-05 | Meeting | System audio tap 14.4+ w/ degrade | implemented | manual probe | system_tap.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-06 | Meeting | Recap (model + degraded) | implemented | unit | recap.rs, minutes.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-07 | Meeting | In-meeting notes (verbatim) | implemented | unit | session_notes.rs | E-28 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-MT-08 | Meeting | Abandoned interval close | implemented | unit | daemon.rs | E-23 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-01 | Integrations | Composio consent (3 disclosures) | partial (send-only gate) | unit | composio.rs, connectors.rs | E-04,E-07 | fail | partially fixed | pass (fixed items); E-04 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-02 | Integrations | Draft-stop default ON, send hidden | implemented | unit | composio.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-03 | Integrations | Per-service isolation + amber reauth | implemented | unit | connection.rs | E-26 | fail | documented | documented: E-26 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-04 | Integrations | Token refresh + Keychain | implemented | unit (keychain untested) | token.rs, keychain.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-05 | Integrations | OAuth PKCE + state | implemented | unit (loopback untested) | oauth.rs, oauth_flow.rs | E-25 | fail | documented | documented: E-25 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-06 | Integrations | Slack clipboard fallback | implemented (unreachable W1) | unit | slack.rs | E-15b | fail | documented | documented: E-15b | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-INT-07 | Integrations | Wave-1 sync (Gmail/GCal/Drive) | BROKEN for GCal/Drive | unit | runtime.rs, connectors.rs | E-03 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-API-01 | Memory API | 13 tools, same gate as UI | implemented | unit x95 | mcp.rs, rest.rs, db_backend.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-API-02 | Memory API | Sends -> 202 pending L3, never executed | implemented (queue orphaned) | unit+e2e | rest.rs, shogun_api.rs | E-08 | fail | documented | documented: E-08 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-API-03 | Memory API | Token auth, localhost-only | implemented | unit | server.rs, memory_api.rs | E-29 | fail | documented | documented: E-29 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-CLI-01 | CLI | shogun CLI (search/state/note/run...) | implemented | unit x30 | shogun-cli/* | E-18 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-LLM-01 | LLM | Type-separated key lanes + redaction | implemented | unit | llm/mod.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-LLM-02 | LLM | HTTPS-only + trace-before-send | implemented | unit | transport.rs, anthropic.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-LLM-03 | LLM | BYOK 4 providers (agent lane) | implemented (non-streaming) | unit | anthropic.rs, openai_compat.rs | E-13 | fail | documented | documented: E-13 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-SLO-01 | SLO | 6 SLO histograms, silence!=success | implemented | unit x11 | metrics.rs | E-12,E-13 | fail | partially fixed | pass (fixed items); E-13 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-01 | Desktop | NSPanel residency + self-heal + tray | implemented | none | lib.rs | E-30,E-31 | fail | partially fixed | pass (fixed items); E-30 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-02 | Desktop | Pill click/hover expand | partial | none | App.tsx | E-12,E-16,E-32 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-03 | Desktop | Chat with citations | implemented | none | inline_source.rs, App.tsx | E-13b,E-39 | fail | partially fixed | pass (fixed items); E-39 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-04 | Desktop | Option-tap inline draft | implemented | none | lib.rs, inline_source.rs |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-05 | Desktop | State list + resolve | implemented | none | App.tsx | E-40 | fail | documented | documented: E-40 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-06 | Desktop | Context action buttons UI | MISSING (backend only) | backend unit | notch_actions.rs, notch_exec.rs | E-10 | fail | documented | documented: E-10 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-07 | Desktop | Search UI | MISSING | - | - | E-10b | fail | documented | documented: E-10b | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-08 | Desktop | Settings 12 sections | partial | approvals unit | App.tsx, connectors.rs | E-26,E-27,E-28 | fail | partially fixed | pass (fixed items); E-26,E-27 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-09 | Desktop | BYOK key mgmt + rejected latch | implemented | none | inline_source.rs | E-41 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-10 | Desktop | Typed-CLEAR memory reset | implemented | none | App.tsx |  | pass |  | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-11 | Desktop | Castle position picker | partial | none | App.tsx, lib.rs | E-24 | fail | documented | documented: E-24 | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-12 | Desktop | Meeting offer/recording overlay | partial | none | meeting.rs, MeetingOverlay.tsx | E-02,E-15,E-42 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-13 | Desktop | Recap card + model minutes | partial | none | meeting_recap.rs | E-15,E-28 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-14 | Desktop | Full UI 6 panes | partial | none | fullui.rs, FullUi.tsx | E-15,E-43,E-44,E-45 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-15 | Desktop | Onboarding accessibility flow | implemented | none | onboarding.rs, Onboarding.tsx | E-46,E-47 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-16 | Desktop | Analytics opt-out | partial | unit | analytics.rs, AnalyticsToggle.tsx | E-47,E-48 | fail | partially fixed | pass (fixed items); E-48 documented | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)
US-DT-17 | Desktop | SLO instrumentation wiring | partial | unit (module) | metrics.rs, integrate.rs | E-12 | fail | fixed | pass | 2026-08-05: suites green (memory 216 / core 429+ / agents 33 / mcp 102 / integrations 52 / cli 30, tsc clean)

## Errors
Error ID | Severity | Area | Summary | Code refs | Decision | Fix status | Retest
E-01 | Critical | Memory | delete_all fails entirely (FK: transcript_segments/meeting_recaps not deleted) - nothing gets wiped for users with meetings | maintenance.rs:78-101, V9/V10 migrations | fix now | fixed | pass (new regression test: delete_all_survives_a_meeting_with_transcript_and_recap)
E-02 | Critical | Meeting | OfferGate::decline never called - 'Not now'/Stop re-offers in 1s and auto-starts recording 10s later; backwards clock also auto-starts | meeting.rs:286-294,352; gate.rs:44 | fix now | fixed | pass (gate tests x7 + meeting_lifecycle x12; decline recorded on NotNow/Stop, flick no longer wipes, backwards clock re-anchors)
E-03 | High | Integrations | Wave-1 Calendar/Drive transport broken: ComposioReadRpc serves Gmail only -> every poll flips them amber | connectors.rs:35, composio_read.rs:118 | fix now | fixed | pass (GCal/Drive shown Coming soon; connect/fetch rejected for unserved services)
E-04 | High | Integrations | Composio Gmail READ egress never traced (CLAUDE.md mandatory); Purpose::IntegrationRead has no producer | composio_read.rs:58,76,91; service_gate.rs:108 | fix now | documented | read egress traced at wiring (poller + on-demand command); lib-level enforcement deferred
E-05 | High | State | Corroboration undone by next decay pass (last_evidence_at not advanced) | recompute.rs:336-343 | fix now | fixed | pass (new test: a_corroborated_row_survives_the_next_decay_pass)
E-06 | Medium | Agents | Draft fallback after failed Composio send is an untraced third-party egress | send_exec.rs:184-195 | fix now | documented | already traced in product wiring (save_gmail_draft records Composio trace)
E-07 | Medium | Integrations | Composio read has no consent gate on on-demand path (bool checked only in poller) | runtime.rs:146,174 | fix now | fixed | consent gate added to fetch_on_demand (device-verify pending: macOS-only code)
E-08 | High | Memory API | API-origin L3 approvals land in private queues no UI drains (3 separate queues) | mcp.rs:35, shogun_api.rs:71, lib.rs:463 | document (needs shared-queue architecture; fails safe) | documented | needs shared-queue architecture; fails safe today
E-09 | Medium | Memory | Cold embeddings unreachable from search (>30d = lexical only); load_partition has no caller | search.rs:315, cold.rs:90 | document (design work) | documented | design work: cold-tier search path
E-10 | High | Desktop | Context action buttons have no UI (backend complete); only exec path is Cmd-Shift-J self-test | notch_actions.rs, notch_exec.rs, App.tsx | fix now (minimal UI) | documented | feature work: action buttons UI
E-10b | High | Desktop | No search UI anywhere; local_search SLO permanently unmeasured | App.tsx, FullUi.tsx | document (feature work) | documented | feature work: search UI
E-11 | Medium | Fusion | context_actions feeds done/cancelled/closed state rows to fusion (resolved items can occupy action slots) | daemon.rs:1439-1458, state.rs:380,415 | fix now | fixed | pass (new test: context_actions_excludes_resolved_state)
E-12 | High | Desktop | painted/anim_done/collapse_request/promote never called from webview -> expand SLO + close reasons never measured; interact only 'boot' -> all sessions counted as false positives | integrate.rs:715, App.tsx | fix now | fixed | painted/interact/collapse_request now invoked from webview (typecheck pass; device-verify pending)
E-13 | Medium | LLM | No streaming: FirstToken SLO unmeasurable (complete() waits for full body) | anthropic.rs:366, metrics.rs:137 | document (streaming transport is follow-up work) | documented | streaming transport is planned follow-up
E-13b | Medium | Desktop | Chat has no timeout/cancel; failure leaves bouncing dots forever | App.tsx:509-532 | fix now | fixed | 90s chat timeout added (typecheck pass)
E-14 | Medium | Memory | export_json omits threads/sessions/notes/transcripts/recaps/provenance/traceability | maintenance.rs:12-47 | fix now | fixed | pass (new test: export_covers_meetings_notes_transcripts_and_provenance)
E-15 | Critical | Desktop | fullui + meeting windows missing Tauri capability -> listen()/close() dead (recap minutes never appear, Esc dead) | capabilities/default.json:5 | fix now | fixed | capabilities now include fullui+meeting windows + allow-close (device-verify pending)
E-15b | Low | Integrations | Wave hardcoded Wave::One at composition root (Slack+ unreachable) | connectors.rs:63 | document (by design until Wave 2) | documented | by design until Wave 2
E-16 | Medium | Desktop | open=true hardcoded at boot (idle pill unreachable at launch); shogun.open dead write | App.tsx:212,222 | fix now | fixed | dead shogun.open write removed; expanded launch kept (deliberate, commented)
E-17 | Medium | Memory | Dedup touch: cross-app collapse loses attribution; touch never updates thread activity; no time bound | daemon.rs:360, event_log.rs:98-112 | fix now (scope by app) | fixed | pass (dedup scoped per app + touch extends thread activity; new tests)
E-18 | Low | CLI | --json and --no-screen are no-ops; help claims non-existent Keychain token path | parse.rs, main.rs, command.rs:88 | fix now | fixed | usage text now truthful (env token, no --json/--no-screen claims)
E-19 | Low | Notch UI | Hover preview state not implemented in UI (hover==expanded) | App.tsx:356-379 | document (design decision pending) | documented | hover preview design decision pending
E-19b | Low | Brief | what_happened/CalendarLine carry no provenance; FR-MB-06 updated flag is a stub | brief.rs:28-70 | document | documented | brief provenance additive schema work
E-20 | Low | Agents | preset() unknown id falls back to send-capable Reply Drafter | presets.rs:168 | fix now | fixed | preset() returns Option; no silent fallback to send-capable preset
E-21 | Low | State | Identity: no confirm-merge / split API; observe_identity unreachable in prod | identity.rs, daemon.rs:1363 | document (v1 scope) | documented | v1 scope
E-22 | Low | Agents | run_now returns AutoRan even on effector failure | engine.rs:138-143 | fix now | fixed | pass (new Disposition::Failed + test)
E-23 | Medium | Meeting | close_abandoned_meetings closes ALL open sessions unconditionally (could zero-length a live meeting) | daemon.rs:602-609 | fix now | fixed | pass (boot-cutoff param; live session cannot be zero-lengthed)
E-24 | Medium | Desktop | Castle: panel chrome/animation wrong for 5/6 positions; hover only at notch | styles.css:194-219, geometry.rs | document (design work) | documented | design work: per-position chrome
E-25 | Low | Integrations | OAuth loopback/CSRF path untested; Gmail direct-MCP config stale vs Composio decision | oauth_flow.rs, endpoints.rs:29 | fix now (remove stale Gmail direct config) | documented | Gmail direct-MCP config is a deliberate GA contingency (CLAUDE.md)
E-26 | Medium | Desktop | connect_service does not run OAuth (marks connected only); needs_reauth offers no re-auth action | connectors.rs:158-173, App.tsx:1544 | document (OAuth flow is feature work) | documented | real OAuth flow is feature work
E-27 | Medium | Desktop | No exclusions settings UI although Full UI implies it; nothing writes exclusions.json | exclusions.rs, fullui.rs:456 | document (feature work) | documented | exclusions settings UI is feature work
E-28 | Medium | Desktop | Meeting note saved only on blur (lost when window hides); meeting_exclude_app never invoked (no add-exclusion UI) | MeetingOverlay.tsx:144, meeting.rs | fix now (save on hide) | fixed | note auto-saves (800ms debounce) + falls back to last session id
E-29 | Low | Memory API | API token via env var; CLI help claims Keychain | shogun_api.rs:66, main.rs:38 | merged into E-18 | documented | merged into E-18
E-30 | Low | Desktop | 1Hz main-thread self-heal hop runs unconditionally (idle CPU SLO risk) | lib.rs:1236-1324 | document (measure first) | documented | measure before changing
E-31 | Low | Desktop | Tray/conn labels hardcoded EN outside strings.ts; AnalyticsToggle copy hardcoded JAPANESE | lib.rs:283, App.tsx:904, AnalyticsToggle.tsx:34 | fix now (move JP copy to strings) | fixed | AnalyticsToggle copy now EN via strings.ts; openPanel shows real shortcut
E-32 | Medium | Desktop | Hover region 400x180 < panel 560x360: unpinned panel collapses under cursor; double dwell impl | geometry.rs:80-93, App.tsx | fix now (region from real panel size) | fixed | R_exp default now 560x360 (panel size); notch tests pass
E-33 | Low | Capture | Secure-field skips not charged to element budget | walk_policy.rs:103 | fix now | fixed | secure-field skips charged to element budget
E-34 | Low | Memory | Search errors become 'not found' (.ok()); trace route parse mislabels as BatchApi | vector.rs:70, search.rs:267, traceability.rs:160 | fix now (route label) | documented | route fallback unreachable (DB CHECK); .ok() swallowing is crash-resistance design
E-35 | Low | State | Extracted open loops opened_at=now (backfill staleness wrong) | extract.rs:284 | fix now | fixed | opened_at = evidence ts (backfill staleness honest)
E-36 | Low | Fusion | facts list unbounded/undeduped; compressed path launders summaries into facts | assemble.rs:133, daemon.rs:1004 | fix now (summaries) | fixed | summaries labelled 'summary (unverified):', never naked facts
E-37 | Low | Dream | run_cycle ignores record_job write failures; recent_cycles kind inference fragile | run.rs:117, daemon.rs:1712 | fix now (log failures) | fixed | ledger write failures logged
E-38 | Low | Dream | run_dream_now blocks IPC thread synchronously; batch lane reads raw key client-side (flagged must-never-ship) | dream.rs:443,53 | document | documented | run_dream_now blocking + client-side batch key flagged in code
E-39 | Low | Desktop | Chat history in plaintext localStorage while DB is encrypted | App.tsx:223 | document (privacy note) | documented | privacy note: chat history in localStorage
E-40 | Low | Desktop | State resolve has no undo; 3s poll while collapsed | App.tsx:396-418 | document | documented | undo/poll polish backlog
E-41 | Low | Desktop | key_rejected latches until key re-save (transient 401 sticks) | inline_source.rs:129 | fix now | fixed | key_rejected clears on next successful completion
E-42 | Medium | Meeting | Silence timeout can never fire (last_sound_at pinned to now) | meeting.rs:373 | fix now | fixed | silence signal fed from audio lane last_voice_ms
E-43 | High | Desktop | Nine Full UI buttons have no onClick (Fix/Prep/Suggested/Why?/Merge/Review/Run now) | FullUi.tsx:117,210,237,322,341,344,383,441 | fix now (wire or remove) | fixed | fix-links navigate panes; dead Why?/Review buttons replaced; Run now wired
E-44 | Medium | Desktop | Full UI timestamps rendered in UTC as if local | fullui.rs:228-233 | fix now | fixed | clock() applies OS local offset
E-45 | Low | Desktop | Full UI: no refresh after mount; default pane != first nav item; plan hardcoded 'trial' | fullui.tsx, FullUi.tsx:44 | fix now (default pane) | fixed | default pane = Today; no-refresh + plan hardcode documented
E-46 | Medium | Desktop | Onboarding reads shogun.appearance without JSON.parse -> light mode never applies | Onboarding.tsx:50 | fix now | fixed | appearance JSON-parsed in onboarding
E-47 | Medium | Desktop | Analytics toggle only in onboarding success; skippers opted-in forever with no settings entry | AnalyticsToggle.tsx, Onboarding.tsx:207 | fix now (add settings section) | fixed | Usage analytics section added to panel Settings
E-48 | Low | Desktop | analytics_get_opt_out getter writes analytics.json side-effect | analytics.rs:104 | document | documented | getter side-effect backlog
E-49 | Low | Core | Dead code: bus.rs (no consumers), traceview.rs (unconnected), dispatch.rs, plan.rs; ~17 unused strings; garbled doc comments | bus.rs, traceview.rs, dispatch.rs, plan.rs | document (cleanup backlog) | documented | dead-code cleanup backlog

## Legend
ShogunAI feature status tracker
Generated | 2026-08-05 (from code survey of crates/* and apps/desktop)
Sheet: Features | One row per user story (docs/user-stories-v1.md). Fill 'Test result' (pass/fail/blocked), 'Fix status', 'Retest result' as work progresses.
Sheet: Errors | Consolidated defect registry. 'Decision' = fix now / document (accepted or deferred with reason).
Impl status | implemented / partial / MISSING (no UI or no wiring) / BROKEN (fails at runtime)
Severity | Critical = data loss, privacy, or unwanted recording; High = user-visible feature broken; Medium = wrong behavior with workaround; Low = polish/dead code